## Action Plan
Task # | Task Description | Details / Subtasks | Responsibility | Start Date | End Date | Status
1 | Understand Assignment Requirements | Review brief and identify required tables, queries, deliverables. | Group | 2025-11-24 | 2025-11-24 | complete
2 | Design Entity Relationship Diagram (ERD) | Map entities, attributes, PK/FK, relationships. | Group | 2025-11-25 | 2025-11-26 | complete
3 | Create Table Plan | Define fields, datatypes, constraints. | Group | 2025-11-27 | 2025-11-27 | complete
4 | Prepare Flowchart / Pseudocode | Outline logic for data generation and key queries. | Group | 2025-11-28 | 2025-11-29 | complete
5 | Build Database in MySQL | Create DB and tables with PKs, FKs, constraints. | NB | 2025-11-30 | 2025-12-01 | complete
6 | Generate and Insert Data | Insert hospitals, doctors, patients, medications, diseases, prescriptions. |  | 2025-12-02 | 2025-12-03 | Not Started
7 | Write Required SQL Queries | Implement listing, filtering, update, insert queries. |  | 2025-12-04 | 2025-12-05 | Not Started
8 | Test Database Functionality | Verify query results, relationships, data integrity. |  | 2025-12-06 | 2025-12-06 | Not Started
9 | Export MySQL Database (.sql) | Use mysqldump to export final DB. |  | 2025-12-07 | 2025-12-07 | Not Started
10 | Prepare GitHub Repository | Upload ERD, planning docs, Excel files, SQL export, README. | Group | 2025-12-08 | 2025-12-09 | Not Started
11 | Final Review and Submission | Ensure all files included and organized. | Group | 2025-12-10 | 2025-12-10 | Not Started

## Gantt Chart
Task | Nov 24 | Nov 25 | Nov 26 | Nov 27 | Nov 28 | Nov 29 | Nov 30 | Dec 01 | Dec 02 | Dec 03 | Dec 04 | Dec 05 | Dec 06 | Dec 07 | Dec 08 | Dec 09 | Dec 10
Understand Assignment Requirements | ■
Design Entity Relationship Diagram (ERD) |  | ■ | ■
Create Table Schema Plan |  |  |  | ■
Prepare Flowchart / Pseudocode |  |  |  |  | ■ | ■
Build Database in MySQL | [6 empty] | ■ | ■
Generate and Insert Data | [8 empty] | ■ | ■
Write Required SQL Queries | [10 empty] | ■ | ■
Test Database Functionality | [12 empty] | ■
Export MySQL Database (.sql) | [13 empty] | ■
Prepare GitHub Repository | [14 empty] | ■ | ■
Final Review and Submission | [16 empty] | ■