## Action Plan
Group |  | Project Name
Project Summary
ACTION PLAN
ACTION | RESPONSIBLE | PRIORITY | STATUS | START DATE | END DATE | NOTES
GOAL #1 <insert goal here>
ERD, schema, Structure | Nick | High | Complete | 2025-11-26 | 2025-11-28
Data generation codes | Mohammed & Ahmed | Medium | Complete | 2025-12-01 | 2025-12-03
Testing and quality assurance | Nick | Medium | In Progress | 2025-11-25 | 2025-12-07
GOAL #2 <insert goal here>
SQL queries | Shantanu & Jaya | Medium | Complete | 2025-12-03 | 2025-12-05
Testing and quality assurance | Nick | Medium | Complete | 2025-11-25 | 2025-12-07
Portfolio and templates | Mohammed & Ahmed | Medium | Complete | 2025-12-04 | 2025-12-05
GOAL #3 <insert goal here>
Comprehensive review and testing | Nick | High | Complete | 2025-12-05 | 2025-12-07

## Settings
PRIORITY OPTIONS | PROGRESS OPTIONS
High | Complete
Medium | On Hold
Low | In Progress
Not Started